## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Setup & Airflow Installation | MUST HAVE | No Dependency | Sadiya Sadaf | Completed
S1 | S1 | US-002 | Dataset Collection & Understanding | MUST HAVE | No Dependency | Rachi | Completed
S2 | S2 | US-003 | ETL Pipeline Design (Extract, Transform, Load) | MUST HAVE | No Dependency | Sadiya Sadaf | Completed
S2 | S2 | US-004 | Data Cleaning & Transformation using Pandas | MUST HAVE | Pandas | Rachi | Completed
S3 | S3 | US-005 | Airflow DAG Creation & Scheduling | MUST HAVE | Airflow | Sadiya Sadaf | Completed
S3 | S3 | US-006 | Retry Mechanism & Logging Implementation | SHOULD HAVE | Airflow | Sadiya Sadaf | Completed
S3 | S3 | US-007 | Email Alerts Configuration | SHOULD HAVE | SMTP | Keerthana | Completed
S4 | S4 | US-008 | Load Data into PostgreSQL | MUST HAVE | PostgreSQL | Sadiya Sadaf | Completed
S4 | S4 | US-009 | Dashboard Development using Streamlit | MUST HAVE | Streamlit | Sadiya Sadaf | Completed
S4 | S4 | US-010 | Deployment using Streamlit Cloud | SHOULD HAVE | GitHub | Keerthana | Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 40 | 40 | 29 | 19 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Setup Airflow using Docker | 2026-02-09 | 2026-02-11 | Sadiya | Setup | Completed | 4 | Day 1: 4; Day 2: 3; Day 3: 2; Day 4: 1; Day 5: 0; Day 6: 0; Day 7: 0
US-002 | 2 | Dataset collection & analysis | 2026-02-12 | 2026-02-13 | Rachi | Research | Completed | 3 | Day 1: 3; Day 2: 2; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-003 | 3 | Design ETL pipeline | 2026-02-14 | 2026-02-17 | Sadiya | Design | Completed | 5 | Day 1: 5; Day 2: 4; Day 3: 3; Day 4: 2; Day 5: 1; Day 6: 0; Day 7: 0
US-004 | 4 | Data cleaning using Pandas | 2026-02-18 | 2026-02-21 | Rachi | Coding | Completed | 6 | Day 1: 6; Day 2: 4; Day 3: 3; Day 4: 2; Day 5: 1; Day 6: 0; Day 7: 0
US-005 | 5 | Create Airflow DAG | 2026-02-22 | 2026-02-24 | Sadiya | Coding | Completed | 4 | Day 1: 4; Day 2: 3; Day 3: 2; Day 4: 1; Day 5: 0; Day 6: 0; Day 7: 0
US-006 | 6 | Add retry & logging | 2026-02-25 | 2026-02-27 | Sadiya | Coding | Completed | 3 | Day 1: 3; Day 2: 2; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-007 | 7 | Configure email alerts | 2026-02-28 | 2026-03-01 | Keerthana | Setup | Completed | 2 | Day 1: 2; Day 2: 1; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
US-008 | 8 | Load data into PostgreSQL | 2026-03-02 | 2026-03-05 | Sadiya | Coding | Completed | 4 | Day 1: 4; Day 2: 3; Day 3: 2; Day 4: 1; Day 5: 0; Day 6: 0; Day 7: 0
US-009 | 9 | Build Streamlit dashboard | 2026-03-06 | 2026-03-10 | Sadiya | Coding | Completed | 6 | Day 1: 6; Day 2: 5; Day 3: 4; Day 4: 3; Day 5: 2; Day 6: 1; Day 7: 0
US-010 | 10 | Deploy dashboard | 2026-03-11 | 2026-03-13 | Keerthana | Deployment | Completed | 3 | Day 1: 3; Day 2: 2; Day 3: 1; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty in Airflow setup | Followed Docker documentation and fixed setup
Sprint 2 | Day 5 | Missing values in dataset | Applied data cleaning using Pandas
Sprint 3 | Day 8 | DAG errors in Airflow | Debugged logs and corrected code
Sprint 3 | Day 9 | Email alerts not triggering | Configured SMTP properly
Sprint 4 | Day 12 | PostgreSQL connection issue | Fixed database connection settings

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-09 | 2026-02-15 | Sadiya Sadaf | Learning Airflow basics | Confusion during setup | Team discussions | Completed Airflow setup successfully
2 | Sprint 2 | 2026-02-16 | 2026-02-22 | Rachi | Writing clean transformation logic | Ignoring data issues | Testing data regularly | Improved data quality using Pandas
3 | Sprint 3 | 2026-02-23 | 2026-03-01 | Sadiya Sadaf | Debugging using logs | Skipping errors | Using Airflow UI | Fixed DAG and pipeline issues
4 | Sprint 4 | 2026-03-02 | 2026-03-10 | Keerthana | Improving dashboard UI | Hardcoding values | Optimization | Successfully deployed dashboard
5
6
7